## Feuil1
Group 18
Simon Wassenius
Calixthe Matteï
Tasks
Task Number | Task Name | Type of Task | Completion (%)
Task 0 | Assembly | Mandatory | 100
| Creation of the Main Assembly |  | 100
Task 1 | Cab | Mandatory | 100
| Door |  | 100
| Windows |  | 100
| Lower Hinges |  | 100
| Upper Hinges |  | 100
Task 2 | Geometry Assurance | Mandatory | 100
| Export the Files in VRML |  | 100
| Positionning in RD&T |  | 100
| Measurements in RD&T |  | 100
| Tolerances in RD&T |  | 100
| Master System Layout |  | 100
| Requirement Drawings |  | 100
| Calculations Pages |  | 100
Task 3 | Bucket | Mandatory | 87.5
| Global Shape |  | 100
| Grooves |  | 100
| Attachments |  | 50
| Teeths |  | 100
Task 4 | CounterweightBody | Mandatory | 30
| Global Design |  | 0
| Bottom Plate |  | 90
| Realistic details |  | 0
Task 5 | Undercarriage | Mandatory | 0
| Interface with wheels |  | 0
| Interface with Counterweight Body |  | 0
Task 6 | Wheels | Mandatory | 66.6667
| Rim |  | 100
| Tyre |  | 100
| Create 4 of them and assemble |  | 0
Task 7 | Arm&Boom | Mandatory | 0
| Arm |  | 0
| Arm's attachment |  | 0
| Boom |  | 0
| Boom's Attachment |  | 0
Task 8 | Constrained AssemblyHydraulic Cylinders | Mandatory | 0
| Fix the Undercarraige |  | 0
| Model Hydraulic Cylinders |  | 0
| Put screws on wheels |  | 0
Task 9 | Rubber sealing | Mandatory | 0
| Create rubber sealing section |  | 0
| Extrude it along the splines |  | 0
Task 10 | FEA | Extra
Task 11 | Use of Knowledgeare | Extra
Task 12 | Realistic Rendering | Extra
Task 13 | Animation | Extra
Task 14 | SheetMetal Design | Extra
Task 15 | Compliant RD&T analysis | Extra
Task 16 | Ergonomic Analysis | Extra
Task 17 | 3D PMI | Extra
Task 18 | Machining | Extra